## Sprint1
Owner | Activity | Action
Akash | What tasks did I work on / complete? | I was working on developing inital code structure setup so that other developer will follow the same standard and process while coding. This task has been completed and code is available on git.
| What am I planning to work on next? | In next sprint I will start working on Payment/passenger UI component.
| What tasks are blocked waiting on another team member? | No Impediments
| XP Value Achieved | Communication
Owner | Activity | Action
Sherin | What tasks did I work on / complete? | I worked on the MySQL Setup in AWS. Also worked on the schema design for entities
| What am I planning to work on next? | I will be working on the backend APIs required for the dashboard screen in the application
| What tasks are blocked waiting on another team member? | There are no blockers currently
| XP Value Achieved | Communication
Owner | Activity | Action
sravani | What tasks did I work on / complete? | worked on the architecture diagram and it is completed
| What am I planning to work on next? | in next sprint i am going to work on ui part for login
| What tasks are blocked waiting on another team member? | no blockings
| XP Value Achieved | weekly cycle
Owner | Activity | Action
Veena Mamidi | What tasks did I work on / complete? | Worked on enabling Continous Integration for the project by enabling jenkins to Git repository
| What am I planning to work on next? | Will work on Profile part of the application
| What tasks are blocked waiting on another team member? | No impediments
| XP Value Achieved | Communication

## Sprint2
Owner | Activity | Action
Akash | What tasks did I work on / complete? | I worked on Payment/Passenger details UI pages. Development of UI pages for the same is done and code is available on git.
| What am I planning to work on next? | I will be working on development of UI container theme for this application.
| What tasks are blocked waiting on another team member? | No Impediments
| XP Value Achieved | Courage
Owner | Activity | Action
Sherin | What tasks did I work on / complete? | I worked on the APIs for inserting flight details to the database and fetching flight data based on source, destination and departure date and also seats availablility based on number of adults and children.
| What am I planning to work on next? | I will be working on the UI screen for dashboard
| What tasks are blocked waiting on another team member? | There are no blockers currently
| XP Value Achieved | Communication
Owner | Activity | Action
sravani | What tasks did I work on / complete? | i worked on login ui page and it is done
| What am I planning to work on next? | i am planning to work on login backend
| What tasks are blocked waiting on another team member? | no blockings
| XP Value Achieved | courage
Owner | Activity | Action
Veena Mamidi | What tasks did I work on / complete? | Brainstormed the components and the fields required for profile
| What am I planning to work on next? | Building components for Profile UI
| What tasks are blocked waiting on another team member? | No impediments
| XP Value Achieved | Simplicity

## Sprint3
Owner | Activity | Action
Akash | What tasks did I work on / complete? | Done with UI container development for application and code is availabel on git.
| What am I planning to work on next? | I will be working on web service development of payment transaction module.
| What tasks are blocked waiting on another team member? | No Impediments. In case of irregularity in application container behavior let me know.
XP Value Achieved
Owner | Activity | Action
Sherin | What tasks did I work on / complete? | I worked on the UI screen for dashboard for showing search results for flights.
| What am I planning to work on next? | I will be working on the webservices related to flight entity.
| What tasks are blocked waiting on another team member? | There are no blockers currently
| XP Value Achieved | Communication
Owner | Activity | Action
sravani | What tasks did I work on / complete? | Done with login ui and working on login backend
| What am I planning to work on next? | planning to work on sigup backend
| What tasks are blocked waiting on another team member? | no blockings
| XP Value Achieved | communication
Owner | Activity | Action
Veena Mamidi | What tasks did I work on / complete? | Building components for Profile UI
| What am I planning to work on next? | Building services for posting User data to database
| What tasks are blocked waiting on another team member? | No impediments
| XP Value Achieved | Communication

## Sprint4
Owner | Activity | Action
Akash | What tasks did I work on / complete? | Development of payment transaction is done
| What am I planning to work on next? | In next sprint, I will be working on Mileage Account UI Part.
| What tasks are blocked waiting on another team member? | No Impediments
| XP Value Achieved | Simplicity
Owner | Activity | Action
Sherin | What tasks did I work on / complete? | I worked on the webservices related to flight entity for adding, updating and deleting flights.
| What am I planning to work on next? | I will be working on the Search Flights related UI screens.
| What tasks are blocked waiting on another team member? | There are no blockers currently
| XP Value Achieved | Respect
Owner | Activity | Action
sravani | What tasks did I work on / complete? | started working on signup backend and it is almost done
| What am I planning to work on next? | in next sprint will be working on signup web services
| What tasks are blocked waiting on another team member? | no blockings
| XP Value Achieved | simplicity
Owner | Activity | Action
Veena | What tasks did I work on / complete? | Having local setup done with MySql server and setting up JDK. Building web services for posting User data to database
| What am I planning to work on next? | Building web services for update booking
| What tasks are blocked waiting on another team member? | There are no blockers currently
| XP Value Achieved | Communication

## Sprint5
Owner | Activity | Action
Akash | What tasks did I work on / complete? | Mileage Account UI development completed and code is available on git. Need to add switch at payment detail page
| What am I planning to work on next? | I will start workign on Mileage Reward Account development in next sprint.
| What tasks are blocked waiting on another team member? | Need to integrate Mileage reward switch on Payment confimation page. I will coordinate with Sherin for integration of mileage in Payment module
| XP Value Achieved | Communication
Owner | Activity | Action
Sherin | What tasks did I work on / complete? | I worked on the UI screens for adding passenger, payment information for booking flight flow.
| What am I planning to work on next? | I will be working on the data flow between the flight booking screens.
| What tasks are blocked waiting on another team member? | There are no blockers currently
| XP Value Achieved | Respect
Owner | Activity | Action
sravani | What tasks did I work on / complete? | i was left with some work in signup backend
| What am I planning to work on next? | planning to work on signup page ui
| What tasks are blocked waiting on another team member? | no blockings
| XP Value Achieved | Respect
Owner | Activity | Action
Veena | What tasks did I work on / complete? | Building web services for update booking
| What am I planning to work on next? | Adding basic Mileage rewards and their calculations in web services
| What tasks are blocked waiting on another team member? | no blockings
| XP Value Achieved | Communication

## Sprint6
Owner | Activity | Action
Akash | What tasks did I work on / complete? | I was working on Mileage rewards web services and it is now woking fine. Some changes are expecting.
| What am I planning to work on next? | I will start working on Employee portal Add flight UI module parallely.
| What tasks are blocked waiting on another team member? | No Impediments
| XP Value Achieved | Courage
Owner | Activity | Action
Sherin | What tasks did I work on / complete? | I worked on passing the selected flight details to the add passenger screen, passenger details to the payment screen and all these deatils in the cofirmation screen.
| What am I planning to work on next? | I will be working on the passenger module for purchasing seats.
| What tasks are blocked waiting on another team member? | There are no blockers currently
| XP Value Achieved | Feedback
Owner | Activity | Action
sravani | What tasks did I work on / complete? | completed signup backend part
| What am I planning to work on next? | planning to work on signup webservices which was left
| What tasks are blocked waiting on another team member? | no blockings
| XP Value Achieved | communication
Owner | Activity | Action
Veena | What tasks did I work on / complete? | Adding basic Mileage rewards and their calculations in web services
| What am I planning to work on next? | Saving booking history and building web services for deleting and altering them
| What tasks are blocked waiting on another team member? | no blockings
| XP Value Achieved | Communication

## Sprint7
Owner | Activity | Action
Akash | What tasks did I work on / complete? | Add Flight Module development is done.
| What am I planning to work on next? | In next sprint, I will start developing web services for Add flight and will also write other related webservices like edit and update flight.
| What tasks are blocked waiting on another team member? | No Impediments.
| XP Value Achieved | Respect
Owner | Activity | Action
Sherin | What tasks did I work on / complete? | I worked on the add passenger module for capturing all the passenger details and selecting Economy or Business class seats. Also worked on availing mileage points and final charges based on the seat selection.
| What am I planning to work on next? | I will be working on the add seats functionality related to flight entity.
| What tasks are blocked waiting on another team member? | There are no blockers currently
| XP Value Achieved | Feedback
Owner | Activity | Action
sravani | What tasks did I work on / complete? | completed signup webservices
| What am I planning to work on next? | planning to work on signup ui
| What tasks are blocked waiting on another team member? | no blockings
| XP Value Achieved | Feedback
Owner | Activity | Action
Veena | What tasks did I work on / complete? | Saving booking history and building web services for deleting and altering them
| What am I planning to work on next? | Handling booking update and building UI for updating flight booking
| What tasks are blocked waiting on another team member? | no blockings
| XP Value Achieved | Communication

## Sprint8
Owner | Activity | Action
Akash | What tasks did I work on / complete? | Edit flight UI and Webservice developement is done and code has been pushed on git.
| What am I planning to work on next? | I will work on validation part of Add flight and edit flight
| What tasks are blocked waiting on another team member? | No Impediments
| XP Value Achieved | Communication
Owner | Activity | Action
Sherin | What tasks did I work on / complete? | I worked on the add seats functionality for add flight AP for employer
| What am I planning to work on next? | I will be working on the payment options for booking flight
| What tasks are blocked waiting on another team member? | There are no blockers currently
| XP Value Achieved | Communication
Owner | Activity | Action
sravani | What tasks did I work on / complete? | completed signup ui and validations
| What am I planning to work on next? | planning to work on header ui development
| What tasks are blocked waiting on another team member? | no blockings
| XP Value Achieved | courage
Owner | Activity | Action
Veena | What tasks did I work on / complete? | Handling booking update and building UI for updating flight booking
| What am I planning to work on next? | Building service and UI for cancel booking
| What tasks are blocked waiting on another team member? | no blockings
| XP Value Achieved | Communication

## Sprint9
Owner | Activity | Action
Akash | What tasks did I work on / complete? | I have added validation for Add/Edit flights
| What am I planning to work on next? | I will be workin on final delivery of product as a whole. I will also work on the integration testing and AWS deployment detup for demo.
| What tasks are blocked waiting on another team member? | All team members will be needed for intergration testings
| XP Value Achieved | Communication
Owner | Activity | Action
Sherin | What tasks did I work on / complete? | I worked on the bank account and credit card payment options for booking flight
| What am I planning to work on next? | I will be working on the final integration testing for the whole application
| What tasks are blocked waiting on another team member? | There are no blockers currently
| XP Value Achieved | Communication
Owner | Activity | Action
sravani | What tasks did I work on / complete? | completed header ui development
| What am I planning to work on next? | done
| What tasks are blocked waiting on another team member? | no blockings
| XP Value Achieved | communication
Owner | Activity | Action
Veena | What tasks did I work on / complete? | Building service and UI for cancel booking
| What am I planning to work on next? | Testing the application with test data
| What tasks are blocked waiting on another team member? | no blockings
| XP Value Achieved | Communication