## sprint 1
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13
28
Requirements and setup | initial code base setup | Akash Kuratkar | 7 | 7 | 5 | 3 | 2 | 1 | 0 | 0
| jenkin setup | Veena Mamidi | 7 | 7 | 6 | 3 | 1 | 1 | 0 | 0
| Architecture Diagram | sai sravani chalasani | 7 | 7 | 5 | 4 | 2 | 2 | 0 | 0
| MYSQL setup on aws | Sherin Thlakulathil Elias | 7 | 7 | 6 | 3 | 2 | 1 | 0 | 0
|  | Total | 28 | 28 | 22 | 13 | 7 | 5 | 0 | 0
Team: |  |  |  | 6 | 5 | 4 | 3 | 2 | 1 | 0
Akash Kuratkar | 7 hours / Week
Sherin Thlakulathil Elias | 7 hours / Week
Veena Mamidi | 7 hours / Week
Sai Sravani Chalasani | 7 hours / Week
Total Available Hours During Sprint: | 28
28 | 22 | 13 | 7 | 2021-10-07: 5; 2021-10-08: 0; 2021-10-09: 0
24 | 20 | 16 | 12 | 2021-10-07: 8; 2021-10-08: 4; 2021-10-09: 0

## sprint 2
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13
28
setup frontend code and Api | Passenger/Payment Details - UI | Akash Kuratkar | 7 | 7 | 5 | 3 | 2 | 1 | 1 | 0
| Profile - UI | Veena Mamidi | 7 | 7 | 6 | 4 | 2 | 1 | 1 | 0
| Login-ui | sai sravani chalasani | 7 | 7 | 5 | 4 | 3 | 2 | 1 | 0
| DashBoard - UI | Sherin Thlakulathil Elias | 7 | 7 | 5 | 4 | 3 | 2 | 1 | 0
|  | Total | 28 | 28 | 24 | 23 | 17 | 13 | 8 | 0
Team:
Akash Kuratkar | 7 hours / Week
Sherin Thlakulathil Elias | 7 hours / Week
Veena Mamidi | 7 hours / Week
Sai Sravani Chalasani | 7 hours / Week
Total Available Hours During Sprint: | 28

## sprint3
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13
28
setup frontend code and Api | UI Design | Akash Kuratkar | 7 | 7 | 5 | 4 | 4 | 2 | 1 | 0
| Profile - Brainstorming the components | Veena Mamidi | 7 | 7 | 4 | 5 | 4 | 2 | 1 | 0
| Login - Backend | sai sravani chalasani | 7 | 7 | 5 | 2 | 2 | 2 | 1 | 0
| DashBoard - Backend | Sherin Thlakulathil Elias | 7 | 7 | 5 | 3 | 2 | 1 | 1 | 0
|  | Total | 28 | 28 | 19 | 14 | 12 | 7 | 4 | 0
Team:
Akash Kuratkar | 7 hours / Week
Sherin Thlakulathil Elias | 7 hours / Week
Veena Mamidi | 7 hours / Week
Sai Sravani Chalasani | 7 hours / Week
Total Available Hours During Sprint: | 28

## sprint4
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13
28
development frontend and api | Transaction-Payment Web Services | Akash Kuratkar | 7 | 7 | 5 | 4 | 4 | 2 | 1 | 0
| user Web Services | Veena Mamidi | 7 | 7 | 4 | 5 | 4 | 2 | 1 | 0
| signup backend | sai sravani chalasani | 7 | 7 | 6 | 4 | 3 | 2 | 1 | 0
| Flight Web Services | Sherin Thlakulathil Elias | 7 | 7 | 3 | 3 | 2 | 1 | 1 | 0
|  | Total | 28 | 28 | 18 | 16 | 13 | 7 | 4 | 0
Team:
Akash Kuratkar | 7 hours / Week
Sherin Thlakulathil Elias | 7 hours / Week
Veena Mamidi | 7 hours / Week
Sai Sravani Chalasani | 7 hours / Week
Total Available Hours During Sprint: | 28

## sprint5
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13
28
development frontend and api | Mileage Rewards Account - UI | Akash Kuratkar | 7 | 7 | 5 | 4 | 4 | 2 | 1 | 0
| Booking - Backend | Veena Mamidi | 7 | 7 | 4 | 5 | 4 | 2 | 1 | 0
| SignUp Web Services | sai sravani chalasani | 7 | 7 | 5 | 2 | 2 | 2 | 1 | 0
| Search Flights- UI | Sherin Thlakulathil Elias | 7 | 7 | 5 | 3 | 2 | 1 | 1 | 0
|  | Total | 28 | 28 | 19 | 14 | 12 | 7 | 4 | 0
Team:
Akash Kuratkar | 7 hours / Week
Sherin Thlakulathil Elias | 7 hours / Week
Veena Mamidi | 7 hours / Week
Sai Sravani Chalasani | 7 hours / Week
Total Available Hours During Sprint: | 28

## sprint6
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13
28
development frontend and api | Signup - ui | Akash Kuratkar | 7 | 7 | 5 | 3 | 2 | 1 | 1 | 0
| Mileage Rewards Account - Backend | Veena Mamidi | 7 | 7 | 6 | 4 | 2 | 1 | 1 | 0
| Signup - Backend | sai sravani chalasani | 7 | 7 | 5 | 4 | 3 | 2 | 1 | 0
| Add passenger, payment and booking workflow | Sherin Thlakulathil Elias | 7 | 7 | 5 | 4 | 3 | 2 | 1 | 0
|  | Total | 28 | 28 | 21 | 15 | 10 | 6 | 4 | 0
Team:
Akash Kuratkar | 7 hours / Week
Sherin Thlakulathil Elias | 7 hours / Week
Veena Mamidi | 7 hours / Week
Sai Sravani Chalasani | 7 hours / Week
Total Available Hours During Sprint: | 28

## sprint7
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13
28
development frontend and api | Add Flight Module Employee | Akash Kuratkar | 7 | 7 | 6 | 6 | 5 | 3 | 2 | 0
| Booking History | Veena Mamidi | 7 | 7 | 5 | 5 | 4 | 2 | 1 | 0
| SignUp Web Services | sai sravani chalasani | 7 | 7 | 2 | 2 | 2 | 2 | 1 | 0
| Add Passenger Module | Sherin Thlakulathil Elias | 7 | 7 | 3 | 3 | 2 | 1 | 1 | 0
|  | Total | 28 | 28 | 16 | 16 | 13 | 8 | 5 | 0
Team:
Akash Kuratkar | 7 hours / Week
Sherin Thlakulathil Elias | 7 hours / Week
Veena Mamidi | 7 hours / Week
Sai Sravani Chalasani | 7 hours / Week
Total Available Hours During Sprint: | 28

## sprint8
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13
28
development frontend and api | Edit Flight(Employee) | Akash Kuratkar | 7 | 7 | 5 | 2 | 1 | 0 | 0 | 0
| Booking -Edit and Cancel functionality | Veena Mamidi | 7 | 7 | 6 | 4 | 3 | 2 | 1 | 0
| SignUp Page UI | sai sravani chalasani | 7 | 7 | 5 | 4 | 3 | 2 | 1 | 0
| Employer Add Flight and Edit Flight | Sherin Thlakulathil Elias | 7 | 7 | 6 | 4 | 2 | 2 | 1 | 0
|  | Total | 28 | 28 | 22 | 14 | 9 | 6 | 3 | 0
Team:
Akash Kuratkar | 7 hours / Week
Sherin Thlakulathil Elias | 7 hours / Week
Veena Mamidi | 7 hours / Week
Sai Sravani Chalasani | 7 hours / Week
Total Available Hours During Sprint: | 28

## sprint9
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13
28
development frontend and api | Add/Edit Flight Validation | Akash Kuratkar | 7 | 7 | 6 | 4 | 3 | 2 | 1 | 0
| CanCel Booking | Veena Mamidi | 7 | 7 | 6 | 5 | 4 | 2 | 0 | 0
| Header Ui Development | sai sravani chalasani | 7 | 7 | 5 | 4 | 2 | 2 | 0 | 0
| Add Payment | Sherin Thlakulathil Elias | 7 | 7 | 5 | 4 | 2 | 1 | 0 | 0
|  | Total | 28 | 28 | 22 | 17 | 11 | 7 | 1 | 0
Team:
Akash Kuratkar | 7 hours / Week
Sherin Thlakulathil Elias | 7 hours / Week
Veena Mamidi | 7 hours / Week
Sai Sravani Chalasani | 7 hours / Week
Total Available Hours During Sprint: | 28