## sprint 1
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13
28
Requirements and setup | initial code base setup | Akash Kuratkar | 7 | 7 | 5 | 3 | 2 | 1 | 0 | 0
| jenkin setup | Veena Mamidi | 7 | 7 | 6 | 3 | 1 | 1 | 0 | 0
| Architecture Diagram | sai sravani chalasani | 7 | 7 | 5 | 4 | 2 | 2 | 0 | 0
| MYSQL setup on aws | Sherin Thlakulathil Elias | 7 | 7 | 6 | 3 | 2 | 1 | 0 | 0
|  | Total | 28 | 28 | 22 | 13 | 7 | 5 | 0 | 0
Team: |  |  |  | 6 | 5 | 4 | 3 | 2 | 1 | 0
Akash Kuratkar | 7 hours / Week
Sherin Thlakulathil Elias | 7 hours / Week
Veena Mamidi | 7 hours / Week
Sai Sravani Chalasani | 7 hours / Week
Total Available Hours During Sprint: | 28

## sprint 2
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13
28
setup frontend code and Api | Passenger/Payment Details - UI | Akash Kuratkar | 7 | 7 | 5 | 3 | 2 | 1 | 1 | 0
| Profile - UI | Veena Mamidi | 7 | 7 | 6 | 4 | 2 | 1 | 1 | 0
| Login-ui | sai sravani chalasani | 7 | 7 | 5 | 4 | 3 | 2 | 1 | 0
| DashBoard - UI | Sherin Thlakulathil Elias | 7 | 7 | 5 | 4 | 3 | 2 | 1 | 0
|  | Total | 28 | 28 | 24 | 23 | 17 | 13 | 8 | 0
Team:
Akash Kuratkar | 7 hours / Week
Sherin Thlakulathil Elias | 7 hours / Week
Veena Mamidi | 7 hours / Week
Sai Sravani Chalasani | 7 hours / Week
Total Available Hours During Sprint: | 28

## sprint3
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13
28
setup frontend code and Api | UI Design | Akash Kuratkar | 7 | 7 | 5 | 4 | 4 | 2 | 1 | 0
| Profile - Brainstorming the components | Veena Mamidi | 7 | 7 | 4 | 5 | 4 | 2 | 1 | 0
| Login - Backend | sai sravani chalasani | 7 | 7 | 5 | 2 | 2 | 2 | 1 | 0
| DashBoard - Backend | Sherin Thlakulathil Elias | 7 | 7 | 5 | 3 | 2 | 1 | 1 | 0
|  | Total | 28 | 28 | 19 | 14 | 12 | 7 | 4 | 0
Team:
Akash Kuratkar | 7 hours / Week
Sherin Thlakulathil Elias | 7 hours / Week
Veena Mamidi | 7 hours / Week
Sai Sravani Chalasani | 7 hours / Week
Total Available Hours During Sprint: | 28

## sprint4
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13
28
development frontend and api | Transaction-Payment Web Services | Akash Kuratkar | 7 | 7 | 5 | 4 | 4 | 2 | 1 | 0
| user Web Services | Veena Mamidi | 7 | 7 | 4 | 5 | 4 | 2 | 1 | 0
| signup backend | sai sravani chalasani | 7 | 7 | 6 | 4 | 3 | 2 | 1 | 0
| Flight Web Services | Sherin Thlakulathil Elias | 7 | 7 | 3 | 3 | 2 | 1 | 1 | 0
|  | Total | 28 | 28 | 18 | 16 | 13 | 7 | 4 | 0
Team:
Akash Kuratkar | 7 hours / Week
Sherin Thlakulathil Elias | 7 hours / Week
Veena Mamidi | 7 hours / Week
Sai Sravani Chalasani | 7 hours / Week
Total Available Hours During Sprint: | 28

## sprint5
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13
28
development frontend and api | Mileage Rewards Account - UI | Akash Kuratkar | 7 | 7 | 5 | 4 | 4 | 2 | 1 | 0
| Booking - Backend | Veena Mamidi | 7 | 7 | 4 | 5 | 4 | 2 | 1 | 0
| SignUp Web Services | sai sravani chalasani | 7 | 7 | 5 | 2 | 2 | 2 | 1 | 0
| Search Flights- UI | Sherin Thlakulathil Elias | 7 | 7 | 5 | 3 | 2 | 1 | 1 | 0
|  | Total | 28 | 28 | 19 | 14 | 12 | 7 | 4 | 0
Team:
Akash Kuratkar | 7 hours / Week
Sherin Thlakulathil Elias | 7 hours / Week
Veena Mamidi | 7 hours / Week
Sai Sravani Chalasani | 7 hours / Week
Total Available Hours During Sprint: | 28

## sprint6
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13
28
development frontend and api | Signup - ui | Akash Kuratkar | 7 | 7 | 5 | 3 | 2 | 1 | 1 | 0
| Mileage Rewards Account - Backend | Veena Mamidi | 7 | 7 | 6 | 4 | 2 | 1 | 1 | 0
| Signup - Backend | sai sravani chalasani | 7 | 7 | 5 | 4 | 3 | 2 | 1 | 0
| Add passenger, payment and booking workflow | Sherin Thlakulathil Elias | 7 | 7 | 5 | 4 | 3 | 2 | 1 | 0
|  | Total | 28 | 28 | 21 | 15 | 10 | 6 | 4 | 0
Team:
Akash Kuratkar | 7 hours / Week
Sherin Thlakulathil Elias | 7 hours / Week
Veena Mamidi | 7 hours / Week
Sai Sravani Chalasani | 7 hours / Week
Total Available Hours During Sprint: | 28

## sprint7
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13
28
development frontend and api | Add Flight Module Employee | Akash Kuratkar | 7 | 7 | 6 | 6 | 5 | 3 | 2 | 0
| Booking History | Veena Mamidi | 7 | 7 | 5 | 5 | 4 | 2 | 1 | 0
| SignUp Web Services | sai sravani chalasani | 7 | 7 | 2 | 2 | 2 | 2 | 1 | 0
| Add Passenger Module | Sherin Thlakulathil Elias | 7 | 7 | 3 | 3 | 2 | 1 | 1 | 0
|  | Total | 28 | 28 | 16 | 16 | 13 | 8 | 5 | 0
Team:
Akash Kuratkar | 7 hours / Week
Sherin Thlakulathil Elias | 7 hours / Week
Veena Mamidi | 7 hours / Week
Sai Sravani Chalasani | 7 hours / Week
Total Available Hours During Sprint: | 28

## sprint8
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13
28
development frontend and api | Edit Flight(Employee) | Akash Kuratkar | 7 | 7 | 5 | 2 | 1 | 0 | 0 | 0
| Booking -Edit and Cancel functionality | Veena Mamidi | 7 | 7 | 6 | 4 | 3 | 2 | 1 | 0
| SignUp Page UI | sai sravani chalasani | 7 | 7 | 5 | 4 | 3 | 2 | 1 | 0
| Employer Add Flight and Edit Flight | Sherin Thlakulathil Elias | 7 | 7 | 6 | 4 | 2 | 2 | 1 | 0
|  | Total | 28 | 28 | 22 | 14 | 9 | 6 | 3 | 0
Team:
Akash Kuratkar | 7 hours / Week
Sherin Thlakulathil Elias | 7 hours / Week
Veena Mamidi | 7 hours / Week
Sai Sravani Chalasani | 7 hours / Week
Total Available Hours During Sprint: | 28

## sprint9
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13
28
development frontend and api | Add/Edit Flight Validation | Akash Kuratkar | 7 | 7 | 6 | 4 | 3 | 2 | 1 | 0
| CanCel Booking | Veena Mamidi | 7 | 7 | 6 | 5 | 4 | 2 | 0 | 0
| Header Ui Development | sai sravani chalasani | 7 | 7 | 5 | 4 | 2 | 2 | 0 | 0
| Add Payment | Sherin Thlakulathil Elias | 7 | 7 | 5 | 4 | 2 | 1 | 0 | 0
|  | Total | 28 | 28 | 22 | 17 | 11 | 7 | 1 | 0
Team:
Akash Kuratkar | 7 hours / Week
Sherin Thlakulathil Elias | 7 hours / Week
Veena Mamidi | 7 hours / Week
Sai Sravani Chalasani | 7 hours / Week
Total Available Hours During Sprint: | 28

## Retrospective
Sprint1
No. | Agenda | What Went Well | What didnt go well | Remaining questions
1 | Tech Stack | Agreeing on tech stack | Took longer time learning technologies and frameworks.
2 | Understanding scope and requriements. | Came up with a design quickly | Ambiguity in requirements
Sprint 2
No. | Agenda | What Went Well | What didnt go well | Remaining questions
1 | Team Collaboration & Contribution | Interaction and communication was easy. | Sometime we spent more time in meetings.
2 | Work Delivery | Equal efforts were found | Delivery was late
Sprint 3
No. | Agenda | What Went Well | What didnt go well | Remaining questions
1 | Productivty | We were able to speed up the time it took us to buid user interaction | integrating work was difficult
2 | Learning Curve | Pairing between new enigneers and core experience team members went really wel. Got to learn a lot. | Had to spent more time to let other undertand the working of module.
Sprint 4
No. | Agenda | What Went Well | What didnt go well | Remaining questions
1 | Time Management | Willingness to work on new stack | We were spending more time on learning frameworks
2 | Meetings. | Mid-sprint meetings | Ambiguity in requirements
Sprint 5
No. | Agenda | What Went Well | What didnt go well | Remaining questions
1 | Time Manangemenet | Good pair programming despite remote work | Brainstorming took lot of time
2 | Understanding scope and requriements. | Good Collaboration | Training and development took more than expected
Sprint 6
No. | Agenda | What Went Well | What didnt go well | Remaining questions
1 | Tech Stack | Improved delivery frequency | Validation of work
2 | Understanding scope and requriements. | Manage to sort quickly | Ambiguity in requirements
Sprint 7
No. | Agenda | What Went Well | What didnt go well | Remaining questions
1 | Tech Stack | Testing gave us valuable insights | Broken pipes between components
2 | Understanding scope and requriements. | On time standups | Stories Failover
Sprint 7
No. | Agenda | What Went Well | What didnt go well | Remaining questions
1 | Tech Stack | Improved collaboration | Underestimating Task
2 | Understanding scope and requriements. | Speedup in delivery | Testing overhead
Sprint 7
No. | Agenda | What Went Well | What didnt go well | Remaining questions
1 | Tech Stack | Taking up more than planned work | Lack of AWS deployment
2 | Understanding scope and requriements. | Improved Quality work | Time required to deploy on Servers